## Entered Data
PM | Data Entered Y/N
Atanacio | Y | MEC BHER EMS | BWP ADMS | SDGE Implementation
Caceres | Y | ANDE-ADMS | Avangrid NY | EC_CELEC-EP
Farah | Y | UNOPS -VN | WB_EVN
Fustar | Y | Lansing BWL | Barbados
Shaeffer | Y | AEP D-Nexus | ATCO
Uluski | Y | Avangrid ADMS | CEATI
Wasley | Y | Belize_ED | TPC | Kosovo (unknown)
Abad | Y | NV Energy | MERALCO

## ESTA_Projects
All Projects
AEP D-Nexus
ANDE
ATCO
Avangrid ADMS
Avangrid NY
Barbados
Belize_ED
BWP ADMS
CEATI
Kosovo
Lansing BWP
MEC BHER EMS
MERALCO
NV Energy
SDGE Implementation
TPC
USTDA_EC_CELEC-EP
UNOPS -VN
WB_EVN
NIPSCO_EMS

## 2025_Chart
2025
|  |  | Total Hours |  | 1990 |  | Actual Hours are in blue color | Actual Hours are in blue color
|  |  | Projected |  |  |  | Q 1 Actual | Actual + Forecast
|  |  | Hours |  | Projected % Loading | Desired % Loading | % loading | % loading
|  | 1 | 975.5 | Atanacio | 49.02% | 75% | 46.33% | 49.02%
|  | 2 | 563 | Alaghehband | 28.29% | 75% | 54.17% | 28.29%
|  | 3 | 1124 | Caceres | 56.48% | 75% | 45.63% | 56.48%
|  | 4 | 59 | Farah | 2.965% | 20% | 11.71% | 2.965%
|  | 5 | 1095 | Fustar | 55.03% | 75% | 70.04% | 55.03%
|  | 6 | 1235.5 | Ocando | 62.09% | 75% | 100.8% | 62.09%
|  | 7 | 811 | Rodas | 40.75% | 75% | 56.94% | 40.75%
|  | 8 | 495 | Saffarpour | 24.87% | 75% | 22.12% | 24.87%
|  | 9 | 1648 | Shaeffer | 82.81% | 75% | 89.09% | 82.81%
|  | 10 | 186.5 | Songpol | 9.372% | 75% | 4.464% | 9.372%
|  | 11 | 844 | Uluski | 42.41% | 75% | 67.46% | 42.41%
|  | 12 | 1491 | Wasley | 74.92% | 75% | 69.05% | 74.92%
|  | 13 | 1632.25 | Abad | 82.02% | 75% | 102.8% | 82.02%
|  |  | 0 | 0 | 0% | 75% | 0% | 0%
|  |  |  | Avg. for Yr | 610.8% | Average YTD | 60.74% | 50.67%
|  |  | 12159.75 |  | Estimate
| Loading | No. of Staff |  |  |  | -6482.25 | Difference | Difference
| 75% | 12 | 18642 |  | Target
0%

## Summary-hours
Summary of All Billable Hours for ESTA Actual and Projections - 2025 & 2026 | [24 empty] | YTD (Q1) Hours, less holidays |  | 504 |  | 0
[6 empty] | Projections | [6 empty] | Projections | [11 empty] | 2025 hours in the year -less holidays |  | 1990
Consultant | 2025 | [11 empty] | 2026 | [11 empty] | YTD | All Year | % loading
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Actual | YTD+Forecast | YTD | YTD+Forecast
Atanacio | 39 | 111 | 83.5 | 100 | 94 | 96 | 88 | 70 | 72 | 76 | 66 | 80 | 62 | 72 | 62 | #REF! | 62 | 72 | 22 | 32 | 22 | 32 | 22 | 24 | 233.5 | 975.5 | 46.33% | 49.02%
Alaghehband | 75 | 85 | 113 | 118 | 84 | 4 | 4 | 16 | 16 | 24 | 8 | 16 | 16 | 24 | 16 | #REF! | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273 | 563 | 54.17% | 28.29%
Caceres | 98 | 62 | 70 | 80 | 58 | 78 | 80 | 58 | 90 | 80 | 180 | 190 | 50 | 40 | 50 | #REF! | 50 | 60 | 50 | 40 | 50 | 40 | 50 | 60 | 230 | 1124 | 45.63% | 56.48%
Farah | 9 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 59 | 11.71% | 2.965%
Fustar | 115 | 138 | 100 | 78 | 64 | 50 | 120 | 82 | 66 | 62 | 126 | 94 | 24 | 28 | 32 | #REF! | 40 | 32 | 48 | 32 | 48 | 44 | 68 | 20 | 353 | 1095 | 70.04% | 55.03%
Ocando | 154.5 | 160 | 193.5 | 145.5 | 132 | 99 | 119 | 40 | 72 | 24 | 40 | 56 | 40 | 20 | 56 | #REF! | 60 | 56 | 32 | 16 | 32 | 16 | 32 | 0 | 508 | 1235.5 | 100.8% | 62.09%
Rodas | 76 | 88 | 123 | 108 | 60 | 48 | 60 | 48 | 60 | 50 | 50 | 40 | 50 | 40 | 50 | #REF! | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 287 | 811 | 56.94% | 40.75%
Saffarpour | 28.5 | 15 | 68 | 39.5 | 72 | 72 | 48 | 48 | 32 | 32 | 20 | 20 | 16 | 16 | 40 | #REF! | 40 | 40 | 16 | 16 | 16 | 16 | 16 | 0 | 111.5 | 495 | 22.12% | 24.87%
Shaeffer | 145 | 162 | 142 | 111 | 168 | 176 | 124 | 124 | 124 | 124 | 124 | 124 | 30 | 30 | 30 | #REF! | 30 | 30 | 16 | 16 | 16 | 16 | 16 | 0 | 449 | 1648 | 89.09% | 82.81%
Songpol | 3 | 1.5 | 18 | 16 | 12 | 12 | 12 | 12 | 12 | 16 | 48 | 24 | 4 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 186.5 | 4.464% | 9.372%
Uluski | 57 | 132 | 151 | 152 | 128 | 80 | 40 | 48 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 844 | 67.46% | 42.41%
Wasley | 129 | 108 | 111 | 103 | 116 | 124 | 132 | 116 | 140 | 96 | 176 | 140 | 108 | 84 | 88 | #REF! | 92 | 72 | 60 | 52 | 60 | 48 | 80 | 40 | 348 | 1491 | 69.05% | 74.92%
Abad | 178.25 | 167 | 173 | 139 | 132 | 163 | 176 | 88 | 128 | 128 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 518.25 | 1632.25 | 102.8% | 82.02%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Total Worked/Forecasted | 1107.25 | 1249.5 | 1376 | 1190 | 1120 | 1002 | 1003 | 750 | 860 | 720 | 918 | 864 | 520 | 474 | 544 | #REF! | 560 | 522 | 414 | 364 | 414 | 372 | 374 | 224 |  |  | 56.92% | 50.67%
Hours/mo | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144
75% Loading Goal | 2025 Jan.: 1584; 2025 Feb.: 1440; 2025 Mar.: 1512; 2025 April: 1584; 2025 May: 1512; 2025 June: 1494; 2025 July: 1716; 2025 August: 1716; 2025 Sept.: 1638; 2025 Oct.: 1716; 2025 Nov.: 1404; 2025 Dec.: 1326
Available | 476.75 | 190.5 | 136 | 394 | 392 | 492 | 713 | 966 | 778 | 996 | 486 | 462 | -520 | -474 | -544 | #REF! | -560 | -522 | -414 | -364 | -414 | -372 | -374 | -224 | Available hours
|  |  |  | Less than 50% |  |  |  |  | Exceed available hours per month | [6 empty] | Less than 50% |  |  |  |  | Exceed available hours per month
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
[25 empty] | 0 | 0
Apostolov | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Brunner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 7.143% | 1.809%
Carr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
DePillis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Guill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 144 | 28.57% | 7.236%
| 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 20 | 150 | 180 | 29.76% | 9.045%
Palermo | 12 | 0 | 0 | 0 | 0 | 8 | 88 | 80 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228 | 268 | 45.24% | 13.47%
Rana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Yankovski | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
P. Campos | 20 | 10 | 20 | 10 | 40 | 20 | 10 | 20 | 10 | 20 | 10 | 40 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 180 | 230 | 35.71% | 11.56%
D. Obadina | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
AMI Subcontractors/ANDE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cepeda | 0 | 0 | 0 | 0 | 0 | 30 | 56 | 28 | 5 | 5 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124
Arcos | 0 | 0 | 0 | 0 | 0 | 5 | 30 | 28 | 10 | 10 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83
Total | 42 | 30 | 30 | 30 | 50 | 83 | 194 | 176 | 275 | 295 | 83 | 123 | 20 | 30 | 20 | 30 | 20 | 40 | 20 | 20 | 20 | 20 | 20 | 30
| 1149.25 | 1279.5 | 1406 | 1220 | 1170 | 1085 | 1197 | 926 | 1135 | 1015 | 1001 | 987 | 540 | 504 | 564 | #REF! | 580 | 562 | 434 | 384 | 434 | 392 | 394 | 254 | #REF!

## AEP D_Nexus
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 2025 Jan.: 0; 2025 Mar.: 1
Alaghehband
Caceres
Farah
Fustar
Ocando
Rodas
Saffarpour
Shaeffer | 2025 Jan.: 98; 2025 Feb.: 62; 2025 Mar.: 70; 2025 April: 60; 2025 May: 70; 2025 June: 70; 2025 July: 70; 2025 August: 70; 2025 Sept.: 70; 2025 Oct.: 70; 2025 Nov.: 70; 2025 Dec.: 70
Songpol
Uluski
Wasley
Abad
0
0
0 | 2026 Jan.: 0; 2026 Feb.: 0; 2026 Mar.: 0; 2026 April: 0; 2026 May: 0; 2026 June: 0; 2026 July: 0; 2026 August: 0; 2026 Sept.: 0; 2026 Oct.: 0; 2026 Nov.: 0; 2026 Dec.: 0
Total | 98 | 62 | 71 | 60 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ANDE_ADMS
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 1 | 2.5 | 6 | 3 | 10 | 20 | 20 | 10 | 20 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 62.5 |  | -62.5
Alaghehband
Caceres | 50 | 60 | 68 | 78 | 50 | 60 | 50 | 40 | 50 | 40 | 50 | 60 | 50 | 40 | 50 | 40 | 50 | 60 | 50 | 40 | 50 | 40 | 50 | 60 | 416 |  | -416
Farah | [24 empty] | 0 |  | 0
Fustar | 2025 Jan.: 0; 2025 Mar.: 0; 2025 May: 8; 2025 July: 16; 2025 Sept.: 16; 2025 Oct.: 16; 2025 Nov.: 40; 2025 Dec.: 8; 2026 May: 8; 2026 July: 16; 2026 Sept.: 16; 2026 Oct.: 16; 2026 Nov.: 40; 2026 Dec.: 8 | 24 |  | -24
Ocando | 0 | 0 | 0 | 0 | 4 | 0 | 16 | 0 | 16 | 0 | 16 | 0 |  |  |  |  | 4 | 0 | 16 | 0 | 16 | 0 | 16 | 0 | 20 |  | -20
Rodas | 50 | 88 | 123 | 108 | 60 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 50 | 40 | 519 |  | -519
Saffarpour | 2025 Feb.: 1.5
Shaeffer | [24 empty] | 0 |  | 0
Songpol | [24 empty] | 0 |  | 0
Uluski | [24 empty] | 0 |  | 0
Wasley | 2025 Mar.: 3; 2025 April: 7; 2025 July: 16; 2025 August: 8; 2025 Sept.: 16; 2025 Oct.: 8; 2025 Nov.: 40; 2025 Dec.: 16; 2026 July: 16; 2026 August: 8; 2026 Sept.: 16; 2026 Oct.: 8; 2026 Nov.: 40; 2026 Dec.: 16 | 26 |  | -26
Abad | [24 empty] | 0 |  | 0
0 | [24 empty] | 0 |  | 0
0 | [24 empty] | 0 |  | 0
0 | [24 empty] | 0 |  | 0
Total | 101 | 152 | 200 | 196 | 132 | 120 | 168 | 98 | 168 | 124 | 206 | 144 | 110 | 100 | 110 | 100 | 122 | 120 | 158 | 108 | 158 | 124 | 206 | 144 | 1067.5 |  | -1067.5
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
Vera | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 20
Palermo
Rana
Yankovski
0
P. Campos | 20 | 10 | 20 | 10 | 40 | 20 | 10 | 20 | 10 | 20 | 10 | 40 | 10 | 20 | 10 | 20 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 10
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total | 30 | 30 | 30 | 30 | 50 | 40 | 20 | 40 | 20 | 40 | 20 | 60 | 20 | 30 | 20 | 30 | 20 | 40 | 20 | 20 | 20 | 20 | 20 | 30

## ATCO_OMS Support
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | 2025 Jan.: 17; 2025 Feb.: 19; 2025 Mar.: 12; 2025 April: 15; 2025 May: 16; 2025 June: 16; 2025 July: 16; 2025 August: 16; 2025 Sept.: 16; 2025 Oct.: 16; 2025 Nov.: 16; 2025 Dec.: 16 |  |  | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 17 | 19 | 12 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Avangrid ADMS
Return to Projects
Summary of All Billable Hours Per Project | [26 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 |  | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 2025 Jan.: 9; 2025 Feb.: 66.5; 2025 Mar.: 27; 2025 April: 9.5 | 112 |  |  | 0
Alaghehband
Caceres | [24 empty] | 0 |  |  | 0
Farah | 2025 Jan.: 8; 2025 Feb.: 20; 2025 Mar.: 30 |  |  |  | 0
Fustar | [27 empty] | 0
Ocando | 2025 Jan.: 8; 2025 Feb.: 29.5; 2025 Mar.: 0; 2025 April: 1 |  |  |  | 0
Rodas | [27 empty] | 0
Saffarpour | 2025 Jan.: 10; 2025 Feb.: 8.5; 2025 Mar.: 42.5; 2025 April: 9.5
Shaeffer | 2025 Jan.: 7; 2025 Feb.: 61; 2025 Mar.: 53; 2025 April: 23; 2025 May: 60; 2025 June: 60 |  |  |  | 0
Songpol | [27 empty] | 0
Uluski | 2025 Jan.: 31; 2025 Feb.: 86; 2025 Mar.: 136; 2025 April: 128; 2025 May: 80; 2025 June: 40 |  |  |  | 0
Wasley | 2025 Jan.: 14; 2025 Feb.: 36; 2025 Mar.: 32; 2025 April: 14 |  |  |  | 0
Abad | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
Total | 87 | 307.5 | 320.5 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Avangrid_NY
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband | 2025 Jan.: 75; 2025 Feb.: 85; 2025 Mar.: 88; 2025 April: 117; 2025 May: 80
Caceres | 2025 Jan.: 6; 2025 Feb.: 2; 2025 Mar.: 2; 2025 April: 2; 2025 May: 8 |  |  | 0
Farah | [26 empty] | 0
Fustar | 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 1 |  |  | 0
Ocando | 2025 Jan.: 51; 2025 Feb.: 51.5; 2025 Mar.: 55; 2025 April: 45; 2025 May: 40 |  |  | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 132 | 138.5 | 145 | 165 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Barbados
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 67 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | 2025 Jan.: 44; 2025 Feb.: 81; 2025 Mar.: 12; 2025 April: 2; 2025 May: 8; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0 |  |  | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | 2025 Jan.: 0; 2025 Feb.: 0 |  |  | 0
Wasley | 2025 Jan.: 23; 2025 Feb.: 20; 2025 Mar.: 6; 2025 April: 2 |  |  | 0
Abad
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 67 | 101 | 18 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2025 | [11 empty] | 2026
Associates | 2025 Jan.: 2024; 2026 Jan.: 2025
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
#REF!
#REF!
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BEL_ED-LF
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley |  | 2 | 11 | 9 | 24 | 32 | 24 | 24 | 40 | 24 | 24 | 12 | 40 | 12 | 12 | 12 | 40 | 12 | [8 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 2 | 11 | 9 | 24 | 32 | 24 | 24 | 40 | 24 | 24 | 12 | 40 | 12 | 12 | 12 | 40 | 12 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## BWP ADMS
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 2025 Oct.: 4; 2025 Nov.: 4; 2025 Dec.: 4 |  |  | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour | [26 empty] | 0
Shaeffer | 2025 July: 8; 2025 August: 8; 2025 Sept.: 8; 2025 Oct.: 8; 2025 Nov.: 8; 2025 Dec.: 8 |  |  | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[25 empty] | 0 | 0 | 0
[25 empty] | Acutal Hours | Budgeted Hours | Remaining Hours
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Apostolov | [26 empty] | 0
Brunner
Carr | [26 empty] | 0
DePillis | [26 empty] | 0
Guill | [26 empty] | 0
0 | [26 empty] | 0
Palermo | [26 empty] | 0
Rana | [26 empty] | 0
Yankovski | [26 empty] | 0
0 | [26 empty] | 0
P. Campos | [26 empty] | 0
D. Obadina | [26 empty] | 0
AMI Subcontractors/ANDE | [26 empty] | 0
Cepeda | [26 empty] | 0
Arcos | [26 empty] | 0
Total | [24 empty] | 0 |  | 0

## CEATI
Return to Projects
| Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
| Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
| Consultant | 2025 | [11 empty] | 2026
|  | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
| Atanacio | [26 empty] | 0
Alaghehband
| Caceres | [24 empty] | 0 |  | 0
| Farah | [24 empty] | 0 |  | 0
0 | Fustar | [24 empty] | 0 |  | 0
| Ocando | [26 empty] | 0
Rodas
Saffarpour
| Shaeffer | [24 empty] | 0 |  | 0
| Songpol | [26 empty] | 0
40 | Uluski | 2025 Feb.: 0; 2025 Mar.: 15; 2025 April: 8; 2025 May: 40; 2025 June: 40; 2025 July: 40; 2025 August: 40; 2025 Sept.: 40 | 0 |  | 0
0 | Wasley | [24 empty] | 0 |  | 0
| Abad | [24 empty] | 0 |  | 0
| 0 | [24 empty] | 0 |  | 0
| 0 | [26 empty] | 0
| 0 | [24 empty] | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
|  | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
| 0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Kosovo
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026 | [13 empty] | 0
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 4 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 |  | 240 | 240
Ocando | [26 empty] | 0
Rodas
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 4 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 |  | 240 | 240
Abad | [26 empty] | 0
0 | 2025 Feb.: 0 |  |  | 0
0 | [26 empty] | 0
0
Total | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 0 | 8 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 0 | 480 | 480
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026 | Acutal Hours | Budgeted Hours | Remaining Hours
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
Apostolov | [24 empty] | 0 | 0 | 0
Brunner | [24 empty] | 0 | 0 | 0
Carr | [24 empty] | 0
DePillis | [26 empty] | 0
Guill | [26 empty] | 0
0 | [26 empty] | 0
Palermo | [26 empty] | 0
Rana | [26 empty] | 0
Yankovski | [26 empty] | 0
0 | [26 empty] | 0
P. Campos | [26 empty] | 0
D. Obadina | [26 empty] | 0
AMI Subcontractors/ANDE | [26 empty] | 0
Cepeda | [26 empty] | 0
Arcos | [26 empty] | 0
Total | [24 empty] | 0 | 0 | 0
0

## Lansing
Return to Projects
Summary of All Billable Hours Per Project | [26 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 |  | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [27 empty] | 0
Alaghehband
Caceres | [27 empty] | 0
Farah | [24 empty] | 0 |  |  | 0
Fustar | 2025 Jan.: 62; 2025 Feb.: 51; 2025 Mar.: 72; 2025 April: 54; 2025 May: 16; 2025 June: 0; 2025 July: 24; 2025 August: 16 |  |  |  | 0
Ocando | [27 empty] | 0
Rodas | [27 empty] | 0
Saffarpour
Shaeffer | [27 empty] | 0
Songpol | [27 empty] | 0
Uluski | 2025 Jan.: 25; 2025 Feb.: 46; 2025 Mar.: 0; 2025 April: 8 |  |  |  | 0
Wasley | [27 empty] | 0
Abad | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
Total | 87 | 97 | 72 | 62 | 16 | 0 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## MEC_BHER
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 23 | 32.5 | 27.5 | 43.5 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [9 empty] | 0
Alaghehband | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 16 | 16 | 24 | 8 | 16 | 16 | 24 | 16 | 16 | [10 empty] | 0
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0 | bar: 2025 Jan.
Ocando | 5 | 0 | 0 | 0 | 4 | 16 | 16 | 24 | 40 | 8 | 8 | 40 | 24 | 4 | 40 | 40 | 40 | [9 empty] | 0
Rodas | [26 empty] | 0
Saffarpour | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 16 | 16 | 4 | 4 |  |  | 24 | 24 | 24 | [9 empty] | 0
Shaeffer | 23 | 20 | 7 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | [9 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | 2025 Jan.: 1; 2025 Feb.: 2; 2025 Mar.: 5; 2025 April: 2; 2025 May: 8; 2025 June: 8; 2025 July: 8; 2025 August: 16; 2025 Sept.: 16; 2026 Mar.: 8; 2026 April: 8; 2026 May: 16 |  |  | 0
Abad | 2025 Jan.: 1.25 |  |  | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | 2026 Jan.: 0; 2026 Feb.: 0; 2026 Mar.: 0; 2026 April: 0; 2026 May: 0; 2026 June: 0; 2026 July: 0; 2026 August: 0; 2026 Sept.: 0; 2026 Oct.: 0; 2026 Nov.: 0; 2026 Dec.: 0 |  |  | 0
Total | 54.25 | 54.5 | 39.5 | 58.5 | 102 | 114 | 114 | 142 | 142 | 102 | 74 | 114 | 94 | 82 | 142 | 142 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Pre-FAT |  |  |  | FAT |  |  |  | SAT |  |  | Parallel Operations |  | MEC CO
[6 empty] | Pre-FAT |  |  |  | FAT |  |  |  | SAT | POps
BHER CO
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## MERALCO
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 2025 Feb.: 0; 2025 April: 7; 2025 May: 16; 2025 June: 16 |  |  | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | 2025 Jan.: 5; 2025 Mar.: 1 |  |  | 0
Fustar | 2025 Jan.: 21; 2025 Feb.: 2; 2025 April: 6; 2025 May: 16; 2025 June: 16 |  |  | 0
Ocando | 2025 April: 1; 2025 May: 16; 2025 June: 16 |  |  | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0 |  |  | 0
Songpol | 2025 Feb.: 2; 2025 Mar.: 1; 2025 May: 8; 2025 June: 8; 2025 July: 8; 2025 August: 8; 2025 Sept.: 8; 2025 Oct.: 8; 2025 Nov.: 8; 2025 Dec.: 8 |  |  | 0
Uluski | 2025 Jan.: 6; 2025 Feb.: 0; 2025 Mar.: 1 |  |  | 0
Wasley | 2025 Jan.: 9; 2025 Feb.: 9; 2025 Mar.: 6; 2025 April: 7; 2025 May: 8; 2025 June: 8; 2025 July: 8; 2025 August: 8; 2025 Sept.: 8; 2025 Oct.: 8; 2025 Nov.: 8; 2025 Dec.: 8 |  |  | 0
Abad | 2025 Jan.: 3; 2025 Feb.: 0.75; 2025 Mar.: 3; 2025 April: 5; 2025 May: 8; 2025 June: 8; 2025 July: 8 |  |  | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 44 | 13.75 | 12 | 26 | 72 | 72 | 24 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## NV Energy
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 2025 May: 8; 2025 June: 8; 2025 July: 8 |  |  | 0
Alaghehband | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 25; 2025 April: 0
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | 2025 Jan.: 90.5; 2025 Feb.: 78; 2025 Mar.: 122.5; 2025 April: 82.5; 2025 May: 68; 2025 June: 67; 2025 July: 71 |  |  | 0
Rodas
Saffarpour | 2025 Jan.: 18.5; 2025 Feb.: 5; 2025 Mar.: 25.5; 2025 April: 2
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | 2025 Jan.: 1; 2025 Feb.: 0; 2025 Mar.: 6; 2025 April: 1; 2025 May: 16; 2025 June: 16; 2025 July: 16 |  |  | 0
Abad | 2025 Jan.: 174; 2025 Feb.: 162; 2025 Mar.: 165; 2025 April: 127; 2025 May: 84; 2025 June: 83; 2025 July: 88 |  |  | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | 2026 Jan.: 0; 2026 Feb.: 0; 2026 Mar.: 0; 2026 April: 0; 2026 May: 0; 2026 June: 0; 2026 July: 0; 2026 August: 0; 2026 Sept.: 0; 2026 Oct.: 0; 2026 Nov.: 0; 2026 Dec.: 0 |  |  | 0
Total | 284 | 245 | 344 | 212.5 | 176 | 174 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SDGE Implementation
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio |  |  |  | 17 | 32 | 24 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar |  |  |  | 3 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  |  | 0
Ocando |  |  |  | 1 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  |  | 0
Rodas | [26 empty] | 0
Saffarpour |  |  |  | 28 | 40 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Shaeffer |  |  |  | 1 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  |  | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley |  |  |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  |  | 0
Abad |  |  |  | 4 | 40 | 72 | 80 | 80 | 120 | 120 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 |  |  | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 54 | 168 | 200 | 176 | 176 | 208 | 208 | 168 | 168 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 128 | 40
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## TPC
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | 6 | 2.5 | 6 | 11 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Alaghehband
Caceres
Farah
Fustar | 0 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 16 | 16 | 40 | 40 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Ocando
Rodas
Saffarpour
Shaeffer
Songpol | 2025 Jan.: 2; 2025 Feb.: 1.5; 2025 Mar.: 10; 2025 April: 8; 2025 May: 4; 2025 June: 4; 2025 July: 4; 2025 August: 4; 2025 Sept.: 4; 2025 Oct.: 8; 2025 Nov.: 48; 2025 Dec.: 24; 2026 Jan.: 4
Uluski
Wasley | 84 | 41 | 40 | 60 | 32 | 32 | 32 | 40 | 40 | 40 | 88 | 88 | 48 | 48 | 40 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Abad
0
0
0
Total | 92 | 45 | 56 | 81 | 44 | 44 | 44 | 52 | 64 | 68 | 180 | 160 | 60 | 56 | 48 | 32 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 274 | 0 | -274
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## USTDA_EC_CELEC-EP
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | 2025 Jan.: 42; 2025 June: 18; 2025 July: 30; 2025 August: 18; 2025 Sept.: 40; 2025 Oct.: 40; 2025 Nov.: 130; 2025 Dec.: 130 |  |  | 0
Farah | [26 empty] | 0
Fustar | 2025 Jan.: 8; 2025 June: 18; 2025 July: 48; 2025 August: 34; 2025 Sept.: 6; 2025 Oct.: 6; 2025 Nov.: 22; 2025 Dec.: 22 |  |  | 0
Ocando | 2025 Jan.: 0 |  |  | 0
Rodas | 2025 Jan.: 26; 2025 June: 8; 2025 July: 10; 2025 August: 8; 2025 Sept.: 10; 2025 Oct.: 10 |  |  | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 76 | 0 | 0 | 0 | 0 | 44 | 88 | 60 | 56 | 56 | 152 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner | 2025 Sept.: 18; 2025 Oct.: 18
Carr
DePillis
Guill | 2025 Sept.: 72; 2025 Oct.: 72
Palermo | 2025 Jan.: 12; 2025 June: 8; 2025 July: 88; 2025 August: 80; 2025 Sept.: 20; 2025 Oct.: 20; 2025 Nov.: 20; 2025 Dec.: 20
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda | 2025 Jan.: 0; 2025 June: 30; 2025 July: 56; 2025 August: 28; 2025 Sept.: 5; 2025 Oct.: 5; 2025 Nov.: 11; 2025 Dec.: 11
Arcos | 2025 Jan.: 0; 2025 June: 5; 2025 July: 30; 2025 August: 28; 2025 Sept.: 10; 2025 Oct.: 10; 2025 Nov.: 32; 2025 Dec.: 32
Vallejo | 2025 Sept.: 130; 2025 Oct.: 130
Total | 2025 Jan.: 12; 2025 June: 43; 2025 July: 174; 2025 August: 136; 2025 Sept.: 255; 2025 Oct.: 255; 2025 Nov.: 63; 2025 Dec.: 63

## Future Project 02
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 03
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total
0

## Future Project 04
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0; 2026 Jan.: 0; 2026 Feb.: 0; 2026 Mar.: 0; 2026 April: 0; 2026 May: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 05
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 06
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 07
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 08
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 09
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| 2024 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | 2025 | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 10
Return to Projects
Summary of All Billable Hours Per Project | [26 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 |  | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2024 | [11 empty] | 2025
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [27 empty] | 0
Alaghehband
Caceres | [27 empty] | 0
Farah | [24 empty] | 0 |  |  | 0
Fustar | [24 empty] | 0 |  |  | 0
Ocando | [27 empty] | 0
Rodas | [27 empty] | 0
Saffarpour | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Shaeffer | [24 empty] | 0 |  |  | 0
Songpol | [27 empty] | 0
Uluski | [24 empty] | 0 |  |  | 0
Wasley | [27 empty] | 0
Abad | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
0 | [27 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2024 Jan.: 2025; 2025 Jan.: 2026
| Jan | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## Future Project 11
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 168 | 160 | 184 | 168 | 168 | 176 | 160 | 184 | 168 | 168 | 160 | 128 | 168 | 160 | 184 | 160 | 176 | 168 | 160 | 184 | 160 | 168 | 160 | 128 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total

## UNOPS_VN
Return to Projects
Summary of All Billable Hours Per Project | [25 empty] | 0 |  | 0
Working Hours per month | 176 | 160 | 168 | 176 | 168 | 166 | 176 | 176 | 168 | 176 | 144 | 136 | 168 | 160 | 176 | 176 | 160 | 176 | 176 | 168 | 168 | 176 | 152 | 144 | Acutal Hours | Budgeted Hours | Remaining Hours
Consultant | 2025 | [11 empty] | 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
Atanacio | [26 empty] | 0
Alaghehband
Caceres | [26 empty] | 0
Farah | [26 empty] | 0
Fustar | [26 empty] | 0
Ocando | [26 empty] | 0
Rodas | [26 empty] | 0
Saffarpour
Shaeffer | [26 empty] | 0
Songpol | [26 empty] | 0
Uluski | [26 empty] | 0
Wasley | [26 empty] | 0
Abad | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
0 | [26 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associates | 2025 Jan.: 2025; 2026 Jan.: 2026
| Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | April | May | June | July | August | Sept. | Oct. | Nov. | Dec.
0 | 2025 Jan.: 0; 2025 Feb.: 0; 2025 Mar.: 0; 2025 April: 0; 2025 May: 0; 2025 June: 0; 2025 July: 0; 2025 August: 0; 2025 Sept.: 0; 2025 Oct.: 0; 2025 Nov.: 0; 2025 Dec.: 0
Apostolov
Brunner
Carr
DePillis
Guill
0
Palermo
Rana
Yankovski
0
P. Campos
D. Obadina
AMI Subcontractors/ANDE
Cepeda
Arcos
Total